## Program Risk Register
CIP Program Risk Register
GridPoint Energy, Inc. (NCR11027) — NERC CIP Program ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
Risk ID | Category | Description | Likelihood | Impact | Rating | Mitigation | Owner | Status
PR-01 | Compliance | Asset changes (solar, new subs) not reflected in CIP-002 | Medium | High | High | Recategorize in Phase 02 before audit | Whitfield | Open
PR-02 | Technical | Vendor remote access into OT without adequate controls | Medium | High | High | CIP-005 IRA/Intermediate System + CIP-013 | Nair | Open
PR-03 | Compliance | Prior lapsed CIP-007 R2 patch cycle recurs | Medium | High | High | Patch-cycle internal controls & monitoring | Bell | Open
PR-04 | Audit | Evidence gaps at RF Compliance Audit | Medium | High | High | RSAW-driven evidence program (Phase 05/07) | Whitfield | Open
PR-05 | Resource | OT security staffing insufficient for scope | Medium | Medium | Medium | Advisory augmentation; prioritize Medium BCS | Reyes | Open
PR-06 | Physical | CIP-014 critical-station identification incomplete | Low | Medium | Medium | Risk assessment + third-party review | Delgado | Open
PR-07 | Governance | CIP Senior Manager delegations undocumented | Low | Medium | Medium | Formal delegation instrument (CIP-003 R1) | Reyes | Open