## Milestones
Engagement Milestone Tracker
GridPoint Energy, Inc. (NCR11027) — NERC CIP Program ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
Phase | Milestone | Target | Owner | Exit Criteria | Status
01 | Program foundation baselined | 2026-03 | Reyes | Charter, Sr Mgr, scope, roadmap approved | Complete
02 | CIP-002 categorization baselined | 2026-04 | Whitfield | BCS list & impact ratings approved | Planned
03 | Policies & personnel program | 2026-05 | Reyes | CIP-003/004 programs documented | Planned
04 | Technical & physical controls implemented | 2026-Q3 | Bell | CIP-005/006/007/010/011/008/009/013 in place | Planned
05 | Internal (mock) assessment complete | 2026-Q4 | Advisory | RSAWs & findings register produced | Planned
06 | Gaps remediated / mitigation plans | 2027-Q1 | Whitfield | Mitigation plans on track; highs closed | Planned
07 | RF audit readiness / package | 2027-Q2 | Reyes | Evidence package signed off | Planned
07 | ReliabilityFirst Compliance Audit | 2027-Q2 | RF | Audit conducted; no violations | Planned
08 | Internal controls program operating | 2027-Q3 | Whitfield | ICP running; obligations met | Planned
09 | Executive reporting & closeout | 2027-Q3 | Reyes | Board briefing; maturity roadmap | Planned