## Implementation Tracker
Control Implementation Tracker (by CIP standard)
GridPoint Energy (NCR11027) — Control Implementation ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
CIP Standard | Requirement | Control | Applies To | Status | Evidence Ref | Owner | Gap Closed
CIP-005 | R1 | Electronic Security Perimeter (3 ESPs / 6 EAPs) | Medium BCS | Implemented | EV-CIP005-* | Nair | GAP-10
CIP-005 | R2 | Interactive Remote Access (Intermediate System + MFA) | Medium BCS | Implemented | EV-CIP005-R2 | Nair | GAP-01(H)
CIP-006 | R1 | Physical Security Perimeters (10 PSPs) | Medium BCS/PACS | Implemented | EV-CIP006-* | Delgado | GAP-04(H)
CIP-006 | R2 | Physical access monitoring (≥90-day logs) | PSPs | Implemented | EV-CIP006-R2 | Delgado | GAP-15/25
CIP-007 | R1 | Ports & services baseline | Medium BCS | Implemented | EV-CIP007-R1 | Bell | GAP-08
CIP-007 | R2 | Patch management (35-day cycle) | Medium BCS | Implemented | EV-CIP007-R2 | Bell | GAP-02(H)/23
CIP-007 | R3 | Malicious code prevention | Medium BCS | Implemented | EV-CIP007-R3 | Bell | —
CIP-007 | R4 | Security event monitoring (SIEM) | Medium BCS/EACMS | Implemented | EV-CIP007-R4 | Bell | GAP-07/31
CIP-007 | R5 | System access control (no shared accts) | Medium BCS | Implemented | EV-CIP007-R5 | Bell | GAP-16
CIP-010 | R1 | Configuration baselines (14) & change mgmt | Medium BCS | Implemented | EV-CIP010-R1 | Bell | GAP-03(H)/33
CIP-010 | R2 | Configuration monitoring | Medium BCS | Implemented | EV-CIP010-R2 | Bell | GAP-09
CIP-010 | R3 | Vulnerability assessment (15-month) | Medium BCS | Implemented | EV-CIP010-R3 | Bell | GAP-17
CIP-010 | R4 | Transient Cyber Assets & Removable Media | TCA/RM | Implemented | EV-CIP010-R4 | Bell | GAP-24
CIP-008 | — | Incident Response Plan (E-ISAC/CISA) | Medium BCS | Implemented | EV-CIP008 | Bell | GAP-13
CIP-009 | — | Recovery Plan & backup | Medium BCS | In Progress | EV-CIP009 | Bell | GAP-12/28 IP
CIP-011 | — | BCSI Information Protection | BCSI | Implemented | EV-CIP011 | Whitfield | GAP-06(H)/29
CIP-013 | — | Supply Chain Risk Management plan | Procurement | Implemented | EV-CIP013 | Nair | GAP-14; GAP-32 IP
CIP-014 | — | Critical-station risk assessment (Northgate) | 1 substation | In Progress | EV-CIP014 | Delgado | —