## Gap Closure
Phase 04 Gap Closure (5 High closed; 28 of 34 cumulative; 6 in progress)
GridPoint Energy (NCR11027) — Control Implementation ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
Gap ID | Standard | Risk | Description | Status | Note
GAP-01 | CIP-005 R2 | High | Vendor IRA lacks Intermediate System / MFA | Closed | Jump host + MFA deployed
GAP-02 | CIP-007 R2 | High | Patch cycle exceeded 35 days | Closed | 35-day cycle + mitigation plans
GAP-03 | CIP-010 R1 | High | Config baselines incomplete | Closed | 14 baselines + change mgmt
GAP-04 | CIP-006 R1 | High | Physical access not fully monitored | Closed | PACS + monitoring at all PSPs
GAP-06 | CIP-011 | High | BCSI handling on file shares | Closed | BCSI protection program
GAP-07 | CIP-007 R4 | Moderate | Event logging gaps on EACMS | Closed | SIEM coverage extended
GAP-08 | CIP-007 R1 | Moderate | Ports & services baseline incomplete | Closed | Documented per BCS
GAP-09 | CIP-010 R2 | Moderate | Config monitoring not automated | Closed | Deviation detection
GAP-10 | CIP-005 R1 | Moderate | ESP documentation not current | Closed | ESP register updated
GAP-13 | CIP-008 | Moderate | IR plan missing E-ISAC/CISA timelines | Closed | 1-hour reporting documented
GAP-14 | CIP-013 | Moderate | Supply-chain plan not finalized | Closed | SCRM plan approved
GAP-15 | CIP-006 R2 | Moderate | Physical log retention short | Closed | ≥90-day retention
GAP-16 | CIP-007 R5 | Moderate | Shared/default accounts | Closed | Removed; individual accounts
GAP-17 | CIP-010 R3 | Moderate | VA not documented | Closed | 15-month paper VA
GAP-19 | CIP-011 | Moderate | BCSI reuse/disposal incomplete | Closed | Reuse/disposal procedure
GAP-23 | CIP-007 R2 | Low | Patch source documentation | Closed | Sources documented
GAP-24 | CIP-010 R4 | Low | TCA/removable media edge cases | Closed | TCA/RM controls
GAP-25 | CIP-006 R1 | Low | Visitor log inconsistencies | Closed | Standardized visitor logs
GAP-31 | CIP-007 R4 | Low | Alerting thresholds not tuned | Closed | Thresholds tuned
GAP-33 | CIP-010 R1 | Low | Baseline change approvals not retained | Closed | Approvals retained
GAP-12 | CIP-009 | Moderate | Recovery plan not updated for new EMS | In Progress | Update underway
GAP-21 | CIP-005 R2 | Moderate | IRA session logging incomplete | In Progress | Logging expansion
GAP-27 | CIP-008 | Low | IR test evidence not retained | In Progress | Test scheduled
GAP-28 | CIP-009 | Low | Backup restoration test overdue | In Progress | Restore test scheduled
GAP-29 | CIP-011 | Low | BCSI labeling | Closed | Labeling standard applied
GAP-32 | CIP-013 | Low | Vendor notification clauses missing | In Progress | Contract amendments