## Executive Risk Register
Executive Residual Risk Register (residual posture: Low & stable)
GridPoint Energy (NCR11027) — Executive Reporting & Program Maturity ¦ ReliabilityFirst ¦ good standing 2028-Q2 ¦ BCSI // Illustrative
ID | Residual Risk | Likelihood | Impact | Residual Rating | Owner | Mitigation
ER-01 | OT patch-management complexity on legacy relay platforms | Medium | High | Medium | Bell | Vendor roadmap; compensating controls; automation (roadmap)
ER-02 | Supply-chain / vendor concentration | Medium | Medium | Medium | Nair | CIP-013 program maturation to Level 4; alternate sourcing
ER-03 | Skilled CIP/OT staff retention | Medium | Medium | Medium | Reyes | Cross-training; documented runbooks; succession planning
ER-04 | Evidence staleness between audits | Low | Medium | Low | Whitfield | Continuous evidence collection via ICP; evidence platform (Y1)
ER-05 | Emerging standards (CIP-015 INSM, cloud/virtualization) | Medium | Medium | Low | Whitfield | Regulatory watch; roadmap early-adoption workstream
Penalty exposure framing: NERC CIP non-compliance up to $1M per violation per day. 0 open Possible Violations.