## MIT Summary
Mitigation Plans — Summary
Metric | Count | Note
Mitigation Plans | 9 | From 9 PNC findings
Closed | 8 | Completed + internally validated
In Progress | 1 | MIT-05 (on schedule)
Overdue | 0 | None
Open High | 0 | None
Self-Reports filed to RF | 2 | MIT-02, MIT-07
TFEs required | 0 | All feasible
Residual risk | Low | Audit-ready

## Mitigation Plan Register
Mitigation Plan Register (9 plans; 8 Closed / 1 In Progress)
GridPoint Energy (NCR11027) — Mitigation & Remediation ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
MIT ID | Source PNC | Standard | Risk | Weakness | Remediation | Owner | Completion Date | Disposition | Status
MIT-01 | PNC-01 | CIP-009 | Moderate | Recovery plan not updated for new EMS | Update & re-approve recovery plan | Bell | 2027-01-20 | Self-Logged | Closed
MIT-02 | PNC-02 | CIP-005 R2 | Moderate | IRA session logging incomplete | Extend session logging to all IRA | Nair | 2027-01-28 | Self-Report (RF) | Closed
MIT-03 | PNC-03 | CIP-008 | Low | IR test evidence not retained | Retain tabletop after-action records | Bell | 2027-01-15 | Self-Logged | Closed
MIT-04 | PNC-04 | CIP-009 | Low | Backup restoration test overdue | Execute & document restore test | Bell | 2027-02-05 | Self-Logged | Closed
MIT-05 | PNC-05 | CIP-013 R2 | Low | Vendor notification clauses missing (2) | Amend contracts w/ notification clauses | Nair | 2027-03-31 | Self-Logged | In Progress
MIT-06 | PNC-06 | CIP-007 R4 | Moderate | Audit-log review documentation gaps | Document periodic log-review process | Bell | 2027-01-22 | Self-Logged | Closed
MIT-07 | PNC-07 | CIP-010 R1 | Moderate | Baseline change approvals missing (2) | Backfill approvals; tighten workflow | Bell | 2027-01-30 | Self-Report (RF) | Closed
MIT-08 | PNC-08 | CIP-006 R2 | Low | PACS clock drift | Sync PACS clocks to NTP | Delgado | 2027-01-12 | Self-Logged | Closed
MIT-09 | PNC-09 | CIP-004 R4 | Low | Quarterly access review unsigned | Obtain signature; enforce sign-off | Lee | 2027-01-10 | Self-Logged | Closed