## Milestones
Remediation Milestone Tracker (sample)
GridPoint Energy (NCR11027) — Mitigation & Remediation ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
MIT ID | Milestone | Target | Actual | Status | Owner
MIT-02 | Logging design updated | 2027-01-10 | 2027-01-09 | Complete | Nair
MIT-02 | Logging deployed to all IRA | 2027-01-24 | 2027-01-23 | Complete | Nair
MIT-02 | Evidence validated | 2027-01-28 | 2027-01-28 | Complete | Whitfield
MIT-07 | Backfill approvals | 2027-01-20 | 2027-01-19 | Complete | Bell
MIT-07 | Tighten change workflow | 2027-01-28 | 2027-01-27 | Complete | Bell
MIT-07 | Evidence validated | 2027-01-30 | 2027-01-30 | Complete | Whitfield
MIT-05 | Draft contract amendments | 2027-02-15 | 2027-02-12 | Complete | Nair
MIT-05 | Counterparty signature | 2027-03-31 |  | In Progress | Nair