## Gap Summary
Baseline Gap Assessment — Summary (118 applicable parts)
Result | Count | %
Applicable requirement parts | 118 | 100%
Met | 84 | 71%
Gaps | 34 | 29%
— High-risk gaps | 6
— Moderate gaps | 15
— Low gaps | 13

## Gap Register
Gap Register — 34 gaps (6 High / 15 Moderate / 13 Low)
GridPoint Energy (NCR11027) — CIP-002 Categorization ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
Gap ID | Standard | Requirement | Risk | Description | Remediation Target Phase | Owner | Status
GAP-01 | CIP-005 | R2 | High | Vendor IRA lacks Intermediate System / MFA at 2 substations | Phase 04 | Nair | Open
GAP-02 | CIP-007 | R2 | High | Patch-evaluation cycle exceeded 35 days on control-center BCS | Phase 04 | Bell | Open
GAP-03 | CIP-010 | R1 | High | Configuration baselines incomplete for 10 Medium substation BCS | Phase 04 | Bell | Open
GAP-04 | CIP-006 | R1 | High | Physical access controls at 1 Medium substation not fully monitored | Phase 04 | Delgado | Open
GAP-05 | CIP-004 | R4/R5 | High | Access authorization/revocation records incomplete | Phase 03 | Lee | Open
GAP-06 | CIP-011 | R1 | High | BCSI handling not applied to engineering file shares | Phase 03 | Whitfield | Open
GAP-07 | CIP-007 | R4 | Moderate | Security event logging gaps on 3 EACMS | Phase 04 | Bell | Open
GAP-08 | CIP-007 | R1 | Moderate | Ports & services baseline incomplete | Phase 04 | Bell | Open
GAP-09 | CIP-010 | R2 | Moderate | Configuration monitoring not automated | Phase 04 | Bell | Open
GAP-10 | CIP-005 | R1 | Moderate | ESP documentation not current for 2 Medium subs | Phase 04 | Nair | Open
GAP-11 | CIP-004 | R2 | Moderate | Role-based training records dispersed | Phase 03 | Lee | Open
GAP-12 | CIP-009 | R1 | Moderate | Recovery plan not updated for new EMS | Phase 04 | Bell | Open
GAP-13 | CIP-008 | R1 | Moderate | IR plan missing E-ISAC/CISA reporting timelines | Phase 04 | Bell | Open
GAP-14 | CIP-013 | R1 | Moderate | Supply-chain risk plan not finalized | Phase 04 | Nair | Open
GAP-15 | CIP-006 | R2 | Moderate | Physical access logging retention short of 90 days | Phase 04 | Delgado | Open
GAP-16 | CIP-007 | R5 | Moderate | Shared/default accounts on 4 PCAs | Phase 04 | Bell | Open
GAP-17 | CIP-010 | R3 | Moderate | Vulnerability assessment not documented (15-month) | Phase 04 | Bell | Open
GAP-18 | CIP-003 | R1 | Moderate | Two policy topics missing from suite | Phase 03 | Reyes | Open
GAP-19 | CIP-011 | R2 | Moderate | BCSI reuse/disposal procedure incomplete | Phase 04 | Whitfield | Open
GAP-20 | CIP-004 | R3 | Moderate | PRA renewal tracking manual | Phase 03 | Lee | Open
GAP-21 | CIP-005 | R2 | Moderate | IRA session logging incomplete | Phase 04 | Nair | Open
GAP-22 | CIP-003 | Att.1 | Low | Low-impact awareness reinforcement undocumented | Phase 03 | Lee | Open
GAP-23 | CIP-007 | R2 | Low | Patch source documentation incomplete | Phase 04 | Bell | Open
GAP-24 | CIP-010 | R4 | Low | TCA/removable media procedure edge cases | Phase 04 | Bell | Open
GAP-25 | CIP-006 | R1 | Low | Visitor log inconsistencies | Phase 04 | Delgado | Open
GAP-26 | CIP-004 | R5 | Low | Revocation timing evidence thin | Phase 03 | Lee | Open
GAP-27 | CIP-008 | R2 | Low | IR test evidence not retained | Phase 04 | Bell | Open
GAP-28 | CIP-009 | R2 | Low | Backup restoration test overdue | Phase 04 | Bell | Open
GAP-29 | CIP-011 | R1 | Low | BCSI labeling inconsistent | Phase 03 | Whitfield | Open
GAP-30 | CIP-003 | Att.1 | Low | Low-impact electronic access controls lightly documented | Phase 03 | Nair | Open
GAP-31 | CIP-007 | R4 | Low | Alerting thresholds not tuned | Phase 04 | Bell | Open
GAP-32 | CIP-013 | R2 | Low | Vendor notification clauses missing in 2 contracts | Phase 04 | Nair | Open
GAP-33 | CIP-010 | R1 | Low | Baseline change approvals not always retained | Phase 04 | Bell | Open
GAP-34 | CIP-002 | R2 | Low | 15-month review calendar not yet formalized | Phase 02 | Whitfield | Open