## PNC Summary
Potential Noncompliance — Summary
Risk | Count | Note
High | 0 | None
Moderate | 4 | PNC-01,02,06,07
Low | 5 | PNC-03,04,05,08,09
TOTAL | 9 | Readiness: Substantially Ready

## PNC Register
Potential Noncompliance (PNC) Findings Register — 9 findings
GridPoint Energy (NCR11027) — Internal (Mock) Assessment ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
PNC ID | Standard | Requirement | Risk | Description | Recommendation | Confirms Gap | Owner | Target | Status
PNC-01 | CIP-009 | — | Moderate | Recovery plan not updated for new EMS | Update recovery plan & re-approve | GAP-12 | Bell | Phase 06 | Open
PNC-02 | CIP-005 | R2 | Moderate | IRA session logging incomplete | Extend session logging to all IRA | GAP-21 | Nair | Phase 06 | Open
PNC-03 | CIP-008 | — | Low | IR test evidence not retained | Retain tabletop after-action records | GAP-27 | Bell | Phase 06 | Open
PNC-04 | CIP-009 | — | Low | Backup restoration test overdue | Execute & document restore test | GAP-28 | Bell | Phase 06 | Open
PNC-05 | CIP-013 | R2 | Low | Vendor notification clauses missing (2 contracts) | Amend contracts with notification clauses | GAP-32 | Nair | Phase 06 | Open
PNC-06 | CIP-007 | R4 | Moderate | Audit-log review documentation gaps | Document periodic log-review process | new | Bell | Phase 06 | Open
PNC-07 | CIP-010 | R1 | Moderate | Two baseline change records missing approvals | Backfill approvals; tighten workflow | new | Bell | Phase 06 | Open
PNC-08 | CIP-006 | R2 | Low | PACS clock drift affecting log timestamps | Sync PACS clocks to NTP | new | Delgado | Phase 06 | Open
PNC-09 | CIP-004 | R4 | Low | One quarterly access review unsigned | Obtain signature; enforce sign-off | new | Lee | Phase 06 | Open