## RSAW Tracker
RSAW Tracker (12 RSAWs)
GridPoint Energy (NCR11027) — Internal (Mock) Assessment ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
RSAW | Standard | Requirements | Determination | PNCs | Evidence Sampled | Reviewer | Status
RSAW-002 | CIP-002 | R1-R2 | Compliant | 0 | Categorization, asset lists | Whitfield | Complete
RSAW-003 | CIP-003 | R1-R2 | Compliant | 0 | Policies, Low plan | Whitfield | Complete
RSAW-004 | CIP-004 | R1-R6 | PNC | 1 (PNC-09) | Training, PRA, access reviews | Whitfield | Complete
RSAW-005 | CIP-005 | R1-R2 | PNC | 1 (PNC-02) | ESP config, IRA logs | Whitfield | Complete
RSAW-006 | CIP-006 | R1-R2 | PNC | 1 (PNC-08) | PSP, PACS logs | Whitfield | Complete
RSAW-007 | CIP-007 | R1-R5 | PNC | 1 (PNC-06) | Ports, patch, logs, accounts | Whitfield | Complete
RSAW-008 | CIP-008 | — | PNC | 1 (PNC-03) | IR plan, test records | Whitfield | Complete
RSAW-009 | CIP-009 | — | PNC | 2 (PNC-01/04) | Recovery plan, backup tests | Whitfield | Complete
RSAW-010 | CIP-010 | R1-R4 | PNC | 1 (PNC-07) | Baselines, change records, VA | Whitfield | Complete
RSAW-011 | CIP-011 | — | Compliant | 0 | BCSI program | Whitfield | Complete
RSAW-013 | CIP-013 | R1-R3 | PNC | 1 (PNC-05) | SCRM plan, contracts | Whitfield | Complete
RSAW-014 | CIP-014 | — | In Progress | — | Risk assessment (Northgate) | Delgado | In Progress