## Gap Closure
Phase 03 Gap Closure (8 gaps addressed; ~26 remain for Phase 04)
GridPoint Energy (NCR11027) — CIP-003/004 ¦ ReliabilityFirst ¦ v1.0 ¦ 2026-03-02 ¦ BCSI // Illustrative
Gap ID | Standard | Risk | Description | Action Taken | Status
GAP-05 | CIP-004 R4/R5 | High | Access authorization/revocation records incomplete | Authorization matrix + 24-hr revocation process + evidence | Closed
GAP-11 | CIP-004 R2 | Moderate | Training records dispersed | Centralized training record system | Closed
GAP-18 | CIP-003 R1 | Moderate | Two policy topics missing | Policy suite completed to 9 topics | Closed
GAP-20 | CIP-004 R3 | Moderate | PRA renewal tracking manual | PRA tracking register with 7-yr due dates | Closed
GAP-22 | CIP-003 Att.1 | Low | Low-impact awareness undocumented | Documented low-impact awareness plan | Closed
GAP-26 | CIP-004 R5 | Low | Revocation timing evidence thin | Revocation workflow + timestamped evidence | Closed
GAP-29 | CIP-011 | Low | BCSI labeling inconsistent | BCSI labeling standard (full handling Phase 04) | Partially Closed
GAP-30 | CIP-003 Att.1 | Low | Low-impact electronic access controls docs | Documented electronic access controls | Closed